## WORKING TEMPLATE
[9 empty] | VUYANI ZIKALALA | YES
| PROJECT NAME HERE |  | PM - PROJECT MANAGER (PERSON RESPONSIBLE FOR THE PROJECT, THE FOUR TECHNICIANS) | [5 empty] | LUDWE MGUGUDO | NO
[9 empty] | NHLAKANIPHO ZAKUZA | POSTPONED
| STAGE | DESCRIPTION | DURATION (Days) | PERSON RESPONSIBLE | START DATE | END DATE | TASK COMPLETION | COMMENT | MXOLISI MTSOLO | CANCELLED
| 1 | APPOINTMENT | 1 | SIKHUMBUZO NXUMALO |  |  |  |  | ZODWA ZUNGU
| 2 | WRITE TO TD AND PMU TO ARRANGE KICK OFF MEETING | 1 | PM |  |  |  |  | NOSIZWE MBONAMBI
|  | SUGGEST MMETING DATES AND TIMES |  | PM |  |  |  |  | SBULELE NXUMALO
|  | MAKE FOLLOW UPS FOR CONFIRMATION AND APPROVAL | 1 | PM |  |  |  |  | MENZI NTULI
EXPECTATIONS |  | GET TO MEET PEOPLE TO WORK WITH FROM THE CLIENT | 1 | [5 empty] | NOKWANDA KUNENE
|  | GET TO IDENTIFY THE SIDE TO WORK ON | [6 empty] | PHUMLA GUNUZA
|  | GET TO KNOW WHAT THE CLIENTS EXPECTATION IS | [6 empty] | NOMONDE PENNISTON
|  | CREATE AND AGREE ON PROJECT TIMELINES | [6 empty] | SIKHUMBUZO NXUMALO
|  | AGREE ON REPORTING INTERVALS | [6 empty] | CONTRACTOR
|  | PICK UP TRFMR PREFIXES AND REQUIREMENT EXISTING NETWORK | [6 empty] | MUNICIPALITY
|  | DRAFT MOU AND NPR LETTER TO SUBMIT TO MUNICIPALITY | 1 | [5 empty] | ESKOM
|  | MUNICIPALITY SENDS LETTER TO ESKOM | 2 | MUNICIPALITY |  |  |  |  | DESIGNER
| 3 | SITE INVESTIGATION - PREMARKETING | [6 empty] | PM
|  | DEFINE SCOPE (WARD/VILLAGE) AND NUMBER OF CONNECTIONS | 1 | DESIGNER |  |  |  |  | QUALITY ENG
|  | SEND REQUEST FOR QUOTATION TO ADMIN |  | DESIGNER
|  | ADMIN SENDS REQUEST FOR QUOTATION TO SUPPLIER | 2 | NOKWANDA KUNENE
|  | ADMIN RECEIVES QUOTIONS FROM SUPPLIERS AND SENDS TO TECHNICAL |  | NOKWANDA KUNENE
|  | TECHNICAL APPOINTS SUITABLE SUPPLIER - NOGOTIATED AND LOWEST | 1 | VUYANI ZIKALALA
|  | PREMARKETING COMMENCES | 5 | CONTRACTOR
|  | PREMARKETING SENDS FILE BACK TO TECHNICAL | 2
|  | START PRELIMINARY DESIGN | 1 | DESIGNER
| 4 | SITE IDENTIFICATION - CONFIRMATION WITH ESKOM | 1 | PM
|  | DRAFT LETTER TO SUBMIT TO ESKOM TO NOTIFY OF PROJECT | 1 | PM
|  | ESKOM TO CONFIRM DAY AND TIME OF THE MEETING | 5 | ESKOM
|  | VISIT SITE WITH ESKOM AND MUNICIPAL REPRESENTETIVE AND ID BOUNDARIES | 1 | PM
|  | ESKOM CONFIRM BOUNDARIES | 7 | ESKOM
| 5 | FOLLOW UP ON STATUS OF NPR AND MOU | 1 | MUNICIPALITY
|  | RECEIVE NPR AND MOU | 1 | MUNICIPALITY
|  | BOOK STAKEHOLDERS MEETING WITH ESKOM | 1 | PM
|  | FINALISE PRELIMINARY DESIGN AND BOQ | 1 | DESIGNER
|  | COMPILE PRESENTATION - PRINT, POWERPOINT, STAKEHOLDERS SHEET | 1 | DESIGNER
| 6 | PRESENT STAKEHOLDERS , GET COMMENTS SHEET, STAKEHOLDERS SIGNATURES | 1 | DESIGNER
| 7 | DRT PRESENTATION BOOKING | 1
|  | REVISE PRESENTATION, INCLUDE COMMENTS, | 1 | DESIGNER
|  | BOOK DRT PRESENTATION | 1 | DESIGNER
|  | CONFIRM DRT PRESENTATION DATE | 5 | ESKOM
|  | DRT PRESENTATION, WITH COMMENTS AND SIGNATURES | 1 | DESIGNER
|  | GENERATE CLAIM AND SEND TO ADMIN TO GENERATE INVOICE | 1 | PM
|  | INVOICE GENERATED BY ADMIN | 1 | NOKWANDA KUNENE
|  | INVOICE DELIVERED TO MUNICIPALITY | 1 | SBULELE NXUMALO
| 8 | SURVEY
|  | CREATE SCOPE FOR SURVEY AND SEND RQF TO ADMIN | 1 | DESIGNER
|  | ADMIN RECEIVES RQF AND SENDS TO SUPPLIER | 2 | NOKWANDA KUNENE
|  | TECHNICAL APPOINTS NEGOTIATED SUPPLIER AND REGRET LETTERS | 1 | VUYANI ZIKALALA
|  | PRINT A0 DRAWINGS TO SUBMIT TO SURVEYOR AND SEND DGN BY EMAIL | 1 | DESIGNER
SURVEYOR STARTS SURVEY WORK
|  | SURVEYOR SENDS BACK SURVEY FILES | 15 | DESIGNER
| 9 | DETAILED DESIGN
|  | COMPLETE DETAILED DESIGN | 7 | DESIGNER
|  | COMPILE QUANTITIES FO INPUT TO DETAILED DESIGN BOQ | 2 | DESIGNER
|  | SUBMIT DETAIL BOQ AND DETAILED DESIGN ON DGN TO TECH MANAGER FOR REVIEW | 1 | DESIGNER
|  | TECH MANAGER DESIGN APPROVAL AND MD REVIEW | 1 | VUYANI ZIKALALA
|  | MARK SLDS/ DDS | 2 | DESIGNER
|  | COMPILE DESIGN PACKAGE | 5 | DESIGNER
|  | SUBMIT DESIGN PACKAGE TO ESKOM | 1 | DESIGNER
|  | DESIGN PACKAGE APPROVED - LETTER FROM ESKOM CONFIRMING | 15 | ESKOM
|  | CREATE SCOPE TO WORK AND COMPILE PART 2 OF TENDER DOCUMENT | 2 | PM
|  | ADMIN TO COMPILE PART 1 OF TENDER DOCUMENT | 7 | NOKWANDA KUNENE
| 10 | TENDER PROCESS
|  | BID SPECIFICATION MEETING | 1 | PM
|  | SUBMISSION OF DRAFT TENDER DOC AND ADVERT TO MUNICIPALITY | 2 | NOKWANDA KUNENE
|  | TENDER ADVERT BY MUNICIPALITY | 1 | MUNICIPALITY
|  | PRINTING OF TENDER DOCUMENTS | 3 | NOKWANDA KUNENE
|  | DELIVER TENDER DOCUMENTS TO CLIENT | 1 | SBULELE NXUMALO
|  | HOSTING OF TENDER BRIEFING | 1 | PM
|  | ATTENDING TO BIDDERS QUIERIES AND ADDENDUM | 7 | PM
|  | TENDER DOCUMENT CLOSING | 1 | PM
|  | TENDER EVALUATION AND EVALUATION REPORT | 1 | PM
|  | TENDER ADJUDICATION | 21 | MUNICIPALITY
| 11 | ISSUE OF INTENTION TO AWARD | 1 | MUNICIPALITY
|  | APPEAL PERIOD AND WRITING OF REGRET LETTERS | 14 | MUNICIPALITY
|  | CONTRACTOR APPOINTMENT AND REGRET LETTERS SENDING | 1 | MUNICIPALITY
|  | SOD TURNING AND MEETING - CONTRACTOR INTRO | 1 | PM
|  | SITE KICK OFF MEETING - CLIENT, ESKOM (PROJECTS, CNC, T&Q) | 1 | PM
|  | CONTRACTOR SITE CAMP AND ACCOMMODATION | 1 | CONTRACTOR
|  | SITE ESTABLISHMENT AND EPWP HIRING | 1 | CONTRACTOR
|  | MATERIAL ORDERING | 2 | CONTRACTOR
|  | CONTRACTOR VERIFIES SURVEY PEGS AND REPORT TO CONSULTANT | 3 | CONTRACTOR
|  | CONTRACTOR SUBMITS SAFETY FILE TO CONSULTANT | 1 | CONTRACTOR
|  | CONSULTANT VERIFIES SAFETY FILE AND REPORT BACK TO CONTRACTOR | 1 | PM
|  | CONTRACTOR CORRECTS WHAT MAY BE WRONG WITH SAFETY FILE | 2 | CONTRACTOR
|  | CONSULTANT SUBMITS SAFETY FILE TO CLIENT | 1 | PM
|  | CONSULTANT REQUESTS CONSTRUCTION PROGRAM, REPORTING STRUCTURE AND INVOICE DATES | 1 | PM
|  | CONTRACTOR SUBMITS REPORING STRUCTURE AND PLAN | 1 | CONTRACTOR
|  | CONSULTANT REVIEWS SUBMITTED CONSTRUCTION PLAN | 1 | PM
| 12 | CONSTRUCTION WORK STARTS | 186 | CONTRACTOR
|  | CONSULTANT CHECKS QUALITY (FREQUENCY PER PROJECT) | 8 | QUALITY ENG
|  | CONSULTANT VERIFIES INVOICE (FREQUENCY PER PROJECT) | 8 | PM
|  | CONSULTANT REPORTS PER INVOICE (FREQUENCY PER PROJECT) | 8 | PM
|  | MONTHLY REPORTS FROM QUALITY TO PM (FREQUENCY PER PROJECT) | 8 | QUALITY ENG
|  | MONTHLY REPORTS FROM PM TO TECH MANAGER - ONCE PER WEEK | 1 | PM
|  | MONTHLY REPORTS FROM PM TO CLIENT | 1 | MUNICIPALITY
|  | COMPILE SCOPE ANDSEND RFQ FOR FINAL MARKETING TO ADMIN | 1 | PM
|  | ADMIN SENDS RFQ TO MARKETING AGENTS | 1 | NOKWANDA KUNENE
|  | ADMIN RECEIVES QUOTIONS FROM SUPPLIERS AND SENDS TO TECHNICAL | 3 | NOKWANDA KUNENE
|  | TECHNICAL APPOINTS SUITABLE SUPPLIER - NOGOTIATED AND LOWEST | 1 | VUYANI ZIKALALA
|  | CONSULTANT SENDS CONTRACTOR PCS FILE | 1 | PM
| 13 | ENS (ENGINEERING NETWORK SCHEMATICS) PROCESS
|  | FILL IN FS APPROVAL FORM AND SEND TO CNC FOR SIGNATURE - DESIGN (DGN ,PDF), SLD'S, COMPLETED CHANGE CONTROL FORM | 1 | PM
|  | ESKOM RECEIVES FS PACK AND APPROVES | 1 | ESKOM
|  | CONSULTANT RECEIVES FS APPROVAL FROM CNC | 3 | PM
|  | CONSULTANT SENDS THE FS PACK TO LAND DEVELOPMENT DEPARTMENT | 1 | PM
|  | ESKOM PERFOMS UPLOADING | 1 | ESKOM
|  | CONSULTANT MAKES FOLLOW UP ON UPLOADING STATUS | 3 | PM
|  | LAND DEV DEPARTMENT RETURNS FS PACK | 1 | ESKOM
|  | CONSULTANT VERIFIES AND PROVIDES FEEDBACK | 1 | PM
|  | LAND DEV DEPARTMENT CONFIRMS NETWORK DIAG WITH CNC | 1 | ESKOM
|  | CONSULTANT MAKES FOLLOW UP FOR SLD APPROVAL | 1 | PM
|  | CNC ISSUES GO AHEAD | 1 | ESKOM
|  | CONSULTANT POPULATES MEMOS AND SENDS TO ESKOM | 1 | PM
|  | CONSULTANT RECEIVES STAMPED DD'S | 1 | ESKOM
|  | CREATE SCOPE OF WORK PER OUTAGE | 1 | PM
|  | REQUESTS OUTAGE ; SCOPE, NATURE, MEMOS ETC. | 1 | PM
|  | CONSULTANT MAKES FOLLOW UP ON DATES | 3 | PM
|  | ESKOM CONFIRMS DATES | 1 | ESKOM
|  | BOOKING OF PREOUTAGE MEETING | 1 | PM
|  | MEETING CONFIRMED | 1 | ESKOM
|  | PRE-OUTAGE MEETING | 1
| 13 | OUTAGES |  | PM
|  | CONTRACTOR COMPILES PCS FILE AND FILLS IC SLIPS AND SENDS TO CONSULTANT | 1 | CONTRACTOR
|  | CONSULTANT VERIFIES DATA | 1 | PM
|  | CONSULTANT SENDS DATA TO ESKOM |  | PM
|  | CLOSE OUT REPORT AND SENDING TO CLIENT AND FUNDER | 5 | PM
Note on D91: Typical Project Duration