## Sheet1
Tasks | Duration | Dates
Creation of entity relationship diagram for database (Continuous modification) | 7 days | 10 Feb - 16 Feb 2020
Creating and normalising relational database tables | 7 days | 17 Feb - 23 Feb 2020
UI Design
Authentication Platform | 02 days | 24 Feb - 25 Feb 2020
Client registration | 02 days | 26 Feb - 27 Feb 2020
Admin Dashboard and Layout | 14 days | 28 Feb - 12 March 2020
Employees CRUD Views(from admin dashboard) | 07 days | 13 March - 19 March 2020
Project CRUD Views | 07 days | 20 March - 26 March 2020
Client Project Request | 04 days | 27 March - 30 March 2020
Client Dashboard | 07 days | 31 March - 06 April 2020
Profile Views(admin, staff, client) | 07 days | 07 April - 13 April 2020
Meeting Requests | 05 days | 14 April - 18 April 2020
Task View for admin | 06 days | 19 April - 24 April 2020
Project View for admin | 04 days | 25 April - 28 April 2020
Project View for staff | 04 days | 29 April - 03 March 2020
Task View for staff | 04 days | 04 April - 07 May 2020
Backend
Authentication backend logic | 07 days | 08 May - 14 May 2020
Client registration logic | 04 days | 15 May - 18 May 2020
Stored Procedures for database queries | 14 days | 19 May - 01 June 2020
Employee CRUD logic | 10 days | 02 June - 11 June 2020
Profile logic | 10 days | 12 June - 21 June 2020
Project CRUD logic | 10 days | 22 June - 01 July 2020
Client Project Request logic | 04 days | 02 July - 05 July 2020
File Upload (for staff, admin,and client) | 14 days | 06 July - 19 July 2020
File Download(for staff, admin and client) | 14 days | 20 July - 02 Aug 2020
Monotoring of Project Requests | 02 days | 03 Aug - 04 Aug 2020
Mornitoring Meeting Requests | 10 days | 05 Aug - 14 Aug 2020
Task Movement logic | 16 days | 15 Aug - 30 Aug 2020
Quality Assurance
Testing | 14 Days | 31 Aug - 13 Sep 2020
Deploying
Deploying Database | 05 days | 14 Sep - 18 Sep 2020
Deploying Application | 07 days | 19 Sep - 25 Sep 2020
Further Testing | 10 days | 26 Sep - 05 Oct 2020